## Slide 1
CRUDE DISTILLATION UNIT · INTEGRITY CASE STUDY
From Failure to Control
Root cause analysis · risk register · permit to work · job safety analysis
One unit. One causal chain. Four deliverables that hand over to each other.
PRESENTED BY · GROUP C (29 MEMBERS)
Abu Omosomi Joy
Iniovosa Michayah Olamide
Abdulkadir Garba Yusuf Aondoakaa
Doochivir Christopher
Notes: Do not open with methodology. Open with the event on slide 2. Confirm before presenting: the official Dangote logo has replaced the slot at top-left.

## Slide 2
TWELVE MONTHS ON ONE CRUDE DISTILLATION UNIT
Three failures. Nobody was hurt.
$23.1M
Direct cost
lost margin and repair
28
Days of lost production
across three events
3
High-potential near misses
H₂S, pool fire, firebox fire
0
Injuries
not entirely by design
The zero is not a result. Two of these three could have killed somebody and did not, for reasons that were not under our control. A hot oil release found no ignition source. A tube ruptured when nobody was standing at the heater. That is luck, and luck is not a barrier.
Figures are indicative, from a constructed teaching case — see Basis and Scope in the handout.
Notes: Say the money and the days before any technical word. Everyone in the room understands loss. Land the last line slowly: luck is not a barrier. That sentence is the reason for the next 40 minutes.

## Slide 3
HOW THE FOUR DELIVERABLES CONNECT
Backward look, forward look, authorisation, execution.
Each deliverable produces what the next one consumes. That is the whole session in one line.
01
Root Cause Analysis
Why did it fail?
Three failures, one template, down to the organisational root.
02
Risk Register
What could still fail?
Five entries, scored twice, every one with a named owner.
03
Permit to Work
Who authorises it?
A control architecture, evidenced by a form.
04
Job Safety Analysis
How is it done safely?
Twelve steps at the hands of a fitter with a spanner.
→ what we learn becomes tracked risk
→ tracked risk generates work on live plant
→ the permit authorises the task
Unit CDU, 120,000 bpsd, medium sour blend
Period 12 months to 30 June 2026
Standards API RP 571 / 580 / 584 / 682 · ISO 45001
Notes: This is the map. Put it up, say the sentence, and come back to it between sections. Three things failed, so we analyse why. What we learn becomes risk that has to be tracked. Tracked risk generates work on live hydrocarbon equipment, so that work has to be authorised. And the permit authorises a task that still has to be done safely by hand.

## Slide 4
01
THE BACKWARD LOOK
Why three things failed
Three different mechanisms — aqueous corrosion, mechanical reliability, high-temperature metallurgy. One analysis template.
Notes: 18 minutes for this section. Slow down on the latent roots — that is where the value is.

## Slide 5
ONE METHOD, APPLIED THREE TIMES
The same seven questions, asked of every failure.
The repetition is deliberate. By the third failure you will be predicting the structure and listening to the content.
A
Event and consequence
What happened, what it cost, who could have been hurt
B
Evidence preserved
What we secured before anything was cleaned or repaired
C
Physical root
What the metal actually did, named per API RP 571
D
Human root
What people did, or did not do, and why it was reasonable to them
E
Latent / system root
What the organisation permitted or never asked for
F
Barrier analysis
What should have stopped it — absent, degraded, or working
G
Corrective actions
Ranked against the hierarchy of controls, not listed at random
Section E is where the value is. A report that stops at C and D is a maintenance record.
Drawn as a logic tree in the handout; the Five Whys chain runs underneath each one as a narrative caption.
Mechanism naming API RP 571 terminology throughout — never the word “corrosion” on its own
Action ranking Eliminate → substitute → engineering → administrative → PPE
Notes: Walk the template once, here, so you never have to explain it again on slides 6, 7 and 8.

## Slide 6
FAILURE 1 OF 3 · E-1103A OVERHEAD CONDENSER · 14 NOV 2025
We inspected the wrong part of this line for years.
Ammonium chloride salt corrosion, progressing to hydrochloric acid attack once free water condensed (API RP 571).
EVENT
Through-wall leak in the upper tube rows and the overhead elbow. Sour hydrocarbon and sour water released at grade; H₂S measured 28 ppm at source. Six days down, $4.2M.
PHYSICAL ROOT
Hygroscopic NH₄Cl salts deposit above the water dew point, pull moisture from the vapour and form a concentrated acidic brine against the wall — localised attack while the bulk stream still looks dry.
HUMAN ROOT
The crude slate moved to a higher-chloride blend and desalter wash water was never increased to match. Overhead chemistry sampling fell from daily to weekly during a staffing gap.
LATENT / SYSTEM ROOT
No Management of Change was raised for the crude slate change — blending was treated as an operating adjustment, not a change. So the corrosion loop review never triggered, and the monitoring locations stayed where the wrong mechanism would show.
THE NUMBERS
Nominal wall
9.53 mm
Retirement limit
4.80 mm
Measured at failure
2.10 mm
Rate, historic
0.12 mm/yr
Rate, final 9 months
1.80 mm/yr
BARRIERS
Chloride cap in blend spec
MOC on feedstock change
Desalter performance
Overhead water wash
Chemistry monitoring (IOW)
Gas detection and unit trip
Mechanism NH₄Cl salt → HCl corrosion, API RP 571
Boot water pH 4.1 against a 5.5–6.5 band
Desalted chloride 41 ptb against ≤ 20 ptb design
Notes: The headline is the whole point: the inspection programme was competent and aimed at the wrong location. A 15-fold step change in corrosion rate was visible in the data. Nobody owned the question. For the engineers: TMLs sat on the bottom of the horizontal run, catching erosion and water drop-out.

## Slide 7
FAILURE 2 OF 3 · P-1104A HEAVY GAS OIL PUMP · 3 MAR 2026
This pump told us three times. Nobody asked why.
Mechanical seal failure on 290 °C hydrocarbon service — loss of containment above the flash point, with contractors 30 m away.
EVENT
The seal failed catastrophically; 2.1 m³ of gas oil at 290 °C released and pooled. Gas detection alarmed, the pump tripped, area ESD initiated. It did not ignite. 18 hours down, $0.9M.
PHYSICAL ROOT
The Plan 11 flush line was blocked with coke fines at the orifice. With no flush the seal chamber lost cooling and pressure margin, the faces ran dry, and the carbon face cracked by thermal shock.
HUMAN ROOT
Three seal failures in eighteen months were each closed as a maintenance job — like-for-like, no investigation. The vibration alarm was acknowledged and reset without a work order.
LATENT / SYSTEM ROOT
No defect elimination process and no bad-actor threshold. Nothing said that three failures in eighteen months is abnormal, so the repeats were never visible as a pattern — only as a series of small, well-handled jobs.
THE NUMBERS
Seal arrangement
API 682 Arr. 1
Vibration at failure
11.4 mm/s
ISO 10816-3 alarm
7.10 mm/s
Failures in 18 months
3
MTBF, achieved / target
6 / 36 mo
BARRIERS
Seal flush (Plan 11)
Dual seal containment
Bad actor / RCA trigger
Vibration alarm response
Ignition control — untested
Gas detection and ESD
Mechanism Seal face thermal shock from loss of flush
Service 290 °C, above the 195 °C flash point
Fix API 682 Arr. 2 dual seal, Plan 53B barrier fluid
Notes: Land the ignition line: ignition control was never tested, because there was no ignition source. That is not a barrier. For the managers: maintenance did nothing wrong on any of the three jobs. The system had no way to add them up.

## Slide 8
FAILURE 3 OF 3 · H-1101 CRUDE CHARGE HEATER · 22 MAY 2026
The instrument that would have seen this coming was switched off.
Creep and stress rupture from localised overheating with internal coke deposition (API RP 571), on a 9Cr-1Mo radiant tube.
EVENT
A Pass 3 radiant tube bulged and ruptured longitudinally. Crude discharged into the firebox and ignited. Heater tripped, emergency depressuring initiated, refractory and adjacent tubes damaged. 21 days down, $18.0M.
PHYSICAL ROOT
A partly plugged burner tip impinged flame on the tube. Coke laid down inside; coke insulates, so heat stayed in the wall instead of reaching the process; metal temperature climbed, which laid down coke faster.
HUMAN ROOT
The Pass 3 tube skin thermocouple failed and was inhibited in the DCS to stop nuisance alarms — eight months before the rupture. Pass flow imbalance had been normalised on the panel.
LATENT / SYSTEM ROOT
Instrument inhibits could be applied indefinitely with no register, no expiry and no risk assessment. A reasonable person solved a real problem, and the organisation provided no mechanism that would ever ask for the measurement back.
THE NUMBERS
Tube material
A335 P9
Design TMT
620 °C
Estimated peak TMT
760 °C
Internal coke layer
6 mm
Diameter increase
6.2%
BARRIERS
Tube metal temperature monitoring
Integrity Operating Window
Condition-based decoking
Pass flow balancing
IR thermography survey
Trip and emergency depressuring
Mechanism Creep / stress rupture, API RP 571
Damage indicator > 3% diameter increase; 6.2% measured
Fix Redundant TMT, inhibit register, API RP 584 IOW
Notes: The strongest line in the deck: a safety-relevant measurement was switched off by a reasonable person solving a reasonable problem, and nothing in the organisation would ever ask for it back. Ask the room: how many inhibits are live on your plant right now, and who could tell you?

## Slide 9
WHAT THE THREE HAVE IN COMMON
Every one had a competent engineering answer and an uncomfortable organisational one underneath it.
Not one of these was caused by somebody being careless on the day.
RCA-01 Overhead
PHYSICAL ROOT
NH₄Cl under-deposit corrosion
LATENT ROOT
Crude slate change without MOC
“Inspecting the wrong location”
RCA-02 Pump seal
PHYSICAL ROOT
Dry-running seal faces
LATENT ROOT
No bad-actor threshold
“Fixing without asking why”
RCA-03 Heater tube
PHYSICAL ROOT
Creep from localised overheating
LATENT ROOT
Inhibit with no expiry
“A measurement switched off”
The finding. Each was caused by a system that permitted a reasonable local decision to remove a barrier permanently, and had no route by which anyone would notice. Fixing three pieces of equipment does not fix that. Everything that follows exists to close it.
Hierarchy of controls Every corrective action ranked — eliminate and substitute before administrative
PPE Appears in none of the three action tables. No respirator prevents a condenser from corroding.
Notes: This is the hinge of the presentation. Pause after 'and had no route by which anyone would notice.'

## Slide 10
02
THE FORWARD LOOK
What could still fail
Three of the five entries are the equipment that just failed. The RCA findings have to land somewhere, on somebody, on a date.
Notes: Seven minutes. The matrix two slides on is what they will remember.

## Slide 11
DELIVERABLE 2 · REGISTER RR-CDU-2026-02
Three of these five are the equipment you just watched fail.
Scored twice — once with no credit for controls, once after them. The gap between the two is what the control spend buys.
RR-01
failed
E-1103A overhead condenser
Under-deposit corrosion perforates tubes — sour hydrocarbon and H₂S at grade
20
CRITICAL
8
MEDIUM
Inspection Engineer
review: Quarterly
RR-02
failed
P-1104A HGO pump
Seal failure releases 290 °C hydrocarbon above its flash point — pool fire
20
CRITICAL
6
MEDIUM
Rotating Equipment Engineer
review: Monthly
RR-03
failed
H-1101 radiant tubes
Creep rupture discharges crude into the firebox with escalation potential
20
CRITICAL
10
HIGH
Fired Heater Specialist
review: Monthly
RR-04
by design
T-1101 flash zone shell
Sulfidation wall loss — catastrophic loss of tower inventory
15
CRITICAL
5
MEDIUM
Inspection Manager
review: Annual
RR-05
no cover
E-1108 cooling water side
Tube leak admits hydrocarbon to the cooling tower — flammable release
12
HIGH
12
HIGH
Utilities Engineer
review: Monthly
RR-05 does not move. Every barrier on that line is broken, overdue or not installed, so none of them earns a reduction. A register that quietly scored it down would be lying — and the identical numbers are the strongest argument for funding it.
Notes: Two columns do the persuasive work. The inherent-to-residual split shows what the controls buy. The owner column is the difference between a register and a wish list — a department name there is a wish list. Full columns in the handout: mechanism, existing barriers, IOW, technique, action dates.

## Slide 12
RISK RANKING · 5 × 5 MATRIX
Four Critical entries become one High and three Medium. One does not move at all.
Solid marker = inherent risk, with no credit for controls. Ringed marker = residual, after the barriers are in place and verified.
1
2
3
4
5
2
4
6
8
10
3
6
9
12
15
4
8
12
16
20
5
10
15
20
25
P1
P2
P3
P4
P5
C1
C2
C3
C4
C5
PROBABILITY
CONSEQUENCE
1
1
2
2
3
3
4
4
5
1
E-1103A overhead condenser
20 Critical → 8 Medium
2
P-1104A HGO pump
20 Critical → 6 Medium
3
H-1101 radiant tubes
20 Critical → 10 High
4
T-1101 flash zone
15 Critical → 5 Medium
5
E-1108 cooling water side
12 High → 12 High
Marker 3 stays High. Marker 5 does not move. A fired heater on crude service carries irreducible consequence — the answer is continued active management, not a lower score.
Notes: This is the graphic the managers will remember. Give it time. Analogy, used once: risk-based inspection is spending your security budget where the exposure actually is, rather than putting one guard on every door. Markers 1 and 2 share the inherent cell at P5/C4 — say so, it looks like an error otherwise.

## Slide 13
03
AUTHORISATION
Controlling the work the register created
Eleven actions on live hydrocarbon equipment. Every one is more dangerous to perform than to leave alone, for the duration of the job.
Notes: Seven minutes. Resist explaining the form. Explain the architecture.

## Slide 14
DELIVERABLE 3 · PTW-SYS-CDU REV 4
A permit to work is not a form. It is who may do what, where, and under what conditions.
A site can have an excellent form and no system. The form is only the evidence that the architecture was applied.
LIFECYCLE
Plan
Assess
Isolate
Test
Issue
Brief
Execute
Suspend
Revalidate
Handback
Close
Audit
PERMIT TYPES
Hot Work Type A · spark or flame
Hot Work Type B · hot surface, vehicle entry
Cold Work · mechanical, no ignition source
Line Breaking · any breach of an envelope
Confined Space · continuous monitoring
Electrical / LOTO · duration of isolation
Excavation · revalidated daily
Working at Height · above 1.8 m
Radiography · per exposure window
ROLES · SEPARATION OF DUTIES
Performing Authority
scope, JSA, controls in the field
Issuing Authority
verifies isolations and gas tests
Area Authority
plant condition, cross-permit conflicts
Isolating Authority
applies and proves isolations
Authorised Gas Tester
all atmospheric testing
Site Controller
SIMOPS and emergency authority
No one person may hold PA and IA on the same permit.
SUPPORTING CERTIFICATES
Isolation certificate
every point listed, locked, proved dead
LOTO register
a personal lock for every exposed person
Confined space entry
atmosphere, standby, rescue plan
Excavation
services located, shoring, access
Radiography
barriers, dose rates, timing
The permit authorises the work. The certificates prove the conditions that make it safe — each signed by a different competent person.
Analogy, used once: owning a key is not the same as being authorised to use it at a particular moment.
Notes: The highlighted lifecycle stages — Isolate, Revalidate, Audit — are what the next slide is about. The pump seal job needs three permit types at once: Cold Work, Line Breaking, Electrical Isolation.

## Slide 15
THE THREE THAT MATTER
Every site has a permit form. Incident histories cluster on the same three failures.
A system that does not address these explicitly is a filing exercise.
01
Cross-referencing and SIMOPS
Two permits, each individually safe, become dangerous together.
A permit map — every live permit plotted on the unit plot plan, on the board and mirrored electronically
A SIMOPS matrix classifying every activity pair green, amber or red
A daily coordination meeting before shift start, chaired by the Site Controller
Cross-reference fields on the permit; the Area Authority signs the deconfliction
02
Shift handover and validity
The night shift inherits an assumption instead of a verified condition.
No permit is valid beyond the shift that issued it — 12 hours maximum, regardless
A permit continuing is suspended and revalidated: the oncoming IA walks the job and re-checks every isolation
Outgoing and oncoming IA review the live permit register face to face at the board
Any permit suspended for an ESD or gas alarm is cancelled, not revalidated. It starts again
03
The audit and assurance loop
Does what was written on the permit match what is happening on the ground?
Level 1 — field verification by the Issuing Authority, every permit, every shift
Level 2 — supervisory spot audit, 10% of live permits, weekly
Level 3 — independent HSE assurance, monthly, plus annual external
Leading indicators tracked monthly — and audit findings become risk register entries
Applied on the live permit A hot work permit 22 m away was suspended for the duration of the line break — red on the SIMOPS matrix, not a judgement call on the day
Notes: These three are chosen because they have the worst incident histories, not because they are hard. If you only have time for one, take shift handover — everybody in the room has lived through it.

## Slide 16
CLOSING THE LOOP · PTW-CDU-2026-0473
One live permit, for a job that came off the register, on the pump that failed.
Cold Work, cross-referenced to Line Break LB-2026-0119 and Isolation Certificate IC-2026-0286.
PERMIT TO WORK · COLD WORK
No. PTW-CDU-2026-0473
Equipment
P-1104A · Heavy Gas Oil Pump
Register ref
RR-02 interim action, pending the TA-2027 dual seal upgrade
Work
Replace seal cartridge; fit filtered flush and chamber pressure transmitter; align and recommission
Valid
06:30 – 18:30, 02 July 2026 — one shift only, 12 h maximum
Isolations
Suction and discharge DBB locked closed, bleeds to closed drain; flush line blocked; M-1104A racked out, 6 personal locks
Gas test
06:05 · LEL 0% · H₂S 0 ppm · O₂ 20.9% · instrument MX6-4471, cal. due 18 Sep 2026
SIMOPS SCREEN
PTW-CDU-2026-0468 scaffolding, pump row B — GREEN PTW-CDU-2026-0471 hot work, pipe rack 4 (22 m) — RED, SUSPENDED
Signatures · PA A. O. Joy 06:10 IA I. M. Olamide 06:25 AA D. Christopher 06:28 AGT A. G. Y. Aondoakaa 06:05
Handback accepted 17:35 · permit cancelled 17:40 · work order closed in CMMS with failure and repair coding 17:45
Two details worth pausing on
A hot work permit 22 metres away was suspended because the SIMOPS matrix said so — not because somebody happened to notice on the day.
And the last line
Closing the work order with failure and repair coding sends this job back into the reliability system — exactly the feedback RCA-02 found missing.
Notes: This slide is the handover moment from Deliverable 3 to Deliverable 4. Rehearse it. The permit authorises the job. It does not perform it. What the fitter actually does is next.

## Slide 17
04
EXECUTION
At the hands of a fitter with a spanner
The seal replacement on the pump that failed, under the permit just issued. Twelve steps, from isolation to handback.
Notes: Five minutes. Do not read all twelve steps — take the four that carry the risk.

## Slide 18
DELIVERABLE 4 · JSA-CDU-2026-0473
Twelve steps. Four still carry risk after every control we have.
Same pump as RCA-02, same register entry as RR-02, same permit as PTW-CDU-2026-0473.
1 Verify
2 LOTO
3 Isolate
4 Drain
5 Purge
6 Break
7 Seal out
8 Clean
9 Seal in
10 Align
11 Start
12 Close
Amber = residual risk still Medium after all controls
3
Verify process isolation
Isolating Authority
HAZARD
16″ suction holds a standing column of hot gas oil at line pressure; a passing valve looks identical to a closed one
CONTROLS
Double block and bleed both sides, locked closed · bleeds cracked to closed drain and watched for 10 minutes with no flow · independent gauge at both ends, not the DCS value
4
Cool down and drain casing
PA + Authorised Gas Tester
HAZARD
Residual hydrocarbon at 290 °C — 95 °C above its flash point; H₂S liberated as it depressures
CONTROLS
Casing verified below 60 °C by contact pyrometer before any fitting is loosened · closed drain only · personal H₂S monitors alarming at 5 ppm · SCBA staged · approach taken upwind
8
Clean seal chamber and flush line
Fitters + HSE Officer
HAZARD
Pyrophoric iron sulfide scale — it self-ignites within seconds of drying in air, with no ignition source present
CONTROLS
Deposits kept wet from the moment the chamber is opened · never dry-brushed, no compressed air · scrapings straight into a sealed drum of water · extinguisher within reach and manned
11
Pressurise and recommission
Operations + PA
HAZARD
A new seal fails more often in its first hour than in the next three years, and people are standing next to it
CONTROLS
Staged pressurisation with everyone clear of the seal plane — nobody in line with the gland · barrier fluid pressure confirmed before the motor starts · vibration within 4 h against the 7.10 mm/s IOW
Notes: Step 8 is the one to dwell on. Most crews have never been shown pyrophoric iron sulfide, and it needs no ignition source at all. If you take one hazard out of this deck into your own plant, take that one.

## Slide 19
HOW TO TELL WHETHER A JSA WAS ACTUALLY WRITTEN
“Wear personal protective equipment” appears nowhere as a control on its own.
An experienced supervisor reads the left column and knows the job was never walked.
WHAT A GENERIC JSA SAYS
WHAT THIS ONE SAYS
4
“Hot surfaces — wear PPE”
Verified below 60 °C by contact pyrometer before any fitting is loosened
5
“Purge the equipment”
Nitrogen asphyxiation named as a hazard, with O₂ monitoring alarming below 19.5%
6
“Be careful of dropped objects”
Far-side bolts slackened first, so the joint opens away from the fitter
8
“Clean the seal chamber”
Pyrophoric scale kept wet, sealed drum, no dry brushing, no compressed air
10
“Align the pump”
Pipe strain checked with a dial gauge on the casing, accept below 0.05 mm
11
“Start the pump”
Nobody stands in line with the gland during first pressurisation
Why it matters PPE is the last line of defence. A JSA that leans on it has run out of ideas earlier in the hierarchy than it should have.
Notes: Fast slide, high impact. Read two of the left-hand entries aloud in a bored voice, then their pair.

## Slide 20
THE CHAIN, CLOSED
The job that fixes the pump also repairs the system that let it fail three times.
Step 12 codes the work order with failure and repair data — the input to the bad-actor register that RCA-02 found missing.
01
Root Cause Analysis
Why did it fail?
Three failures, one template, down to the organisational root.
02
Risk Register
What could still fail?
Five entries, scored twice, every one with a named owner.
03
Permit to Work
Who authorises it?
A control architecture, evidenced by a form.
04
Job Safety Analysis
How is it done safely?
Twelve steps at the hands of a fitter with a spanner.
→ what we learn becomes tracked risk
→ tracked risk generates work on live plant
→ the permit authorises the task
RCA-02 → RR-02 → PTW-CDU-2026-0473 → JSA-CDU-2026-0473 → CMMS → bad-actor register → RCA
One pump, all the way round. The loop does not end at the repair — it ends by feeding the next analysis.
Notes: Return to the map one last time. This is the transition into the ask.

## Slide 21
WHAT WE ARE ASKING FOR
Four decisions, four owners.
Three of these cost almost nothing. The one that costs money is the one that stops an $18 million failure repeating.
01
Make crude slate change an MOC trigger
With corrosion loop review as a required step. This is the control missing in RCA-01, and it is a change to a procedure, not to the plant.
Procedure only · Two weeks HSE & Technical Safety Manager
02
Open an instrument inhibit register
Mandatory expiry, risk assessment at application, weekly management review of everything live. Eight months of silence killed a heater tube.
No capital · One month Instrument Engineer
03
Set a bad-actor threshold
Two failures in twelve months triggers an automatic RCA, reviewed monthly. P-1104A failed three times and the system had no way to add them up.
No capital · One month Maintenance Manager
04
Fund the three actions on RR-05
Hydrocarbon-in-cooling-water analyser, biocide dosing loop repair, overdue eddy current inspection. It is the one register entry that has not moved.
~$420k indicative · Q3–Q4 2026 Utilities Engineer
Three failures cost $23.1 million in twelve months. Three of these four asks are procedural and cost nothing but attention.
Notes: Close on decisions, not summary. Do not re-list what you covered. Say the last line and stop talking. Let them ask the first question.

## Slide 22
REFERENCE
Acronyms, standards, and where the detail lives.
Every acronym in this deck was defined on the slide where it first appeared. This is the safety net.
ACRONYMS
AGT Authorised Gas Tester
CDU Crude Distillation Unit
CMMS Maintenance Management System
DBB Double Block and Bleed
ESD Emergency Shutdown
HGO Heavy Gas Oil
IOW Integrity Operating Window
JSA Job Safety Analysis
LEL Lower Explosive Limit
LOC Loss of Containment
LOTO Lock Out Tag Out
MOC Management of Change
MTBF Mean Time Between Failures
PTW Permit to Work
RBI Risk-Based Inspection
RCA Root Cause Analysis
SIMOPS Simultaneous Operations
TML Thickness Monitoring Location
TMT Tube Metal Temperature
ptb Pounds per thousand barrels
STANDARDS REFERENCED
API RP 571
Damage mechanisms in refining
API RP 580 / 581
Risk-based inspection
API RP 584
Integrity operating windows
API RP 573
Inspection of fired heaters
API 682
Pump shaft sealing systems
API 579-1 / ASME FFS-1
Fitness-for-service
ISO 10816-3
Mechanical vibration evaluation
ISO 45001
OH&S management systems
The handout carries the full artefacts: three complete RCAs with barrier analysis and ranked corrective actions · the full risk register with mechanisms, barriers, IOWs and action dates · the PTW system description and live permit · all twelve JSA steps
Group C (29 Members) · Thank you — questions
Notes: Leave this up during questions. The glossary removes the anxiety that stops non-technical attendees from asking.